## Sheet1
| October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  |  | April
Task | 6th | 13th | 20th | 27th | 3rd | 10th | 17th | 24th | 1st | 8th | 15th | 22nd | 29th | 5th | 12th | 19th | 26th | 2nd | 9th | 16th | 23rd | 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th
Background reading
Get dirt diving footage
Software planning
Software Development
Dirt diving, 90°
Separate skydivers from background
Approximate skydivers skeletons
Map skeleton positions to formations
Unforseen problems
Dirt diving, 45°
Separate skydivers from background
Approximate skydivers skeletons
Map skeleton positions to formations
Unforseen problems
In sky, 45°
Account for dynamic background
Account for relative levels
Unforseen problems
Finalise code
Report writing
First draft
Second draft
Final report
Progress report
First draft
Final report
Note on K2: 9th December Deadline: Progress Report
Note on AE2: 28th April Deadline: Final Report